## 1. Product Overview
Item | Description
Product Name | InsightPrism
Product Vision/ Purpose | To convert documents into dashboard for insights
Business Goals / Key Success factors | Automate Document Processing
Primary Stakeholders | Small and medium entrprises

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | Document Ingestion | US1 | Single Upload: Establishing the core pipeline to move a PDF/Image into the OCR engine for text extraction. | File upload system, OCR engine | Must Have | 8 | To Do | Backend Dev Team | Validate file upload and OCR extraction accuracy | QA Team
E2 | Data Structuring Engine | US2 | Batch Upload: Scaling the system to handle multiple files simultaneously using background processing | Batch upload handling | Must Have | 8 |  | Backend Dev Team | Test multi-file upload and processing | QA Team
E3 | Dashboard Generation | US3 | Auto-Structuring: The "Brain." Mapping raw text into specific fields like "Total," "Date," and "Vendor Name." | Entity extraction, schema mapping | Must Have | 13 |  | AI/ML Team | Validate field extraction accuracy (amount, date, vendor) | QA Team
E4 | Export & Integrations | US4 | Error Detection: Adding a validation layer that flags low-confidence data for human review | Validation + confidence scoring | Should have | 8 |  | AI/ML Team | Check incorrect/missing fields handling | QA Team
E5 | Alerts & Insights | US5 | KPI Dashboard: Aggregating extracted data into visual charts (Spend trends, vendor counts, etc.). | Data visualization module | Must Have | 13 | In Progress | Frontend Dev Team | Verify charts and KPI accuracy | QA Team
E6 | UI/UX | US6 | Real-time Updates: Implementing event-driven triggers so the dashboard refreshes automatically as docs process. | Event-driven updates | Should have | 8 |  | Frontend Dev Team | Test real-time refresh | QA Team
Notes: | MoSCoW
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
|  | Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.
Story Points
|  | Fibonacci | 0,1,1,2,3,5,8,13,21,34,….
|  | (Modified) | 0,1,1,2,3,5,8,13,20 (points decided based on a User Story's complexity, effort needed & riks)
Ends at 20. Rarely extended to 40 and 100 for very large tasks.

## 3. Roadmap
Release |  | Key Features | Dependencies | Demo Status
Llist Epic Names
v0.1 | 2025-11-15 | Authentication, Dashboard MVPCore Ingestion & Auth: Implement OCR engine (US1) and map basic fields like Amount/Vendor (US3) for the Dashboard MVP | None | On Track
v0.2 | 2025-11-22 | Bulk Ops & Export: Roll out batch upload handling (US2) and the Excel/CSV export module. | Requires API upgrade | Planned
v0.3 | 2025-11-29 |  |  | Planned
v0.4 | 2025-12-06 |  |  | Planned
v0.5 | 2025-12-13 |  |  | Yet to Plan
v1.0 | 2025-12-20 |  |  | Yet to Plan
v1.1 | 2025-12-27 |  |  | Yet to Plan

## 4. Retrospective
Note: This is for the team to learn and improve. I have taught you in the class on Nov 4, 2025.
Ideally, the team should do this at the end of every release. How often you do , I leave it to you.
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Net time what will you do differently
Strong team collaboration with clear understanding of document processing workflow | OCR accuracy and data extraction had inconsistencies for complex documents | Improve model accuracy and add validation/confidence scoring | Tech Lead